| MISSION LOCATION |  | MISSION CODE |  |
| --- | --- | --- | --- |
| MISSION DATES |  |  |  |

| TIME TO MISSION | ACTION TO COMPLETE | ACTIONER | DATE COMPLETED |
| --- | --- | --- | --- |
| 16 weeks | Approval of Mission | PEVDAC |  |
| 16 weeks | Approval of Mission and Mission Team Roles | PEVDAC |  |
| 15 weeks | Research hotel arrangements, report to Managing Director | Mission Leader |  |
| 14 weeks | Call for participants .pdf and website page update | Managing Director (MD) |  |
| 10 weeks | Deadline for participant call submissions | Prospective workers |  |
| 10 weeks less 1 day | VDWoB applications to Mission and Team Leaders | MD |  |
| 10 weeks less 4 days | Applications reviewed by Mission and Team Leaders | Mission and Team Leaders |  |
| 10 weeks less 5 days | Prospective worker decisions to Managing Director | Mission Leader |  |
| 9 weeks | Notification to workers of acceptance. Email information on airports, flight suggestions, hotels. | MD |  |
| 8 weeks | Reservations for flights and hotels to be made | Participants |  |
| 8 weeks | Evaluation of supplies needed and requisition of supplies to Mission Leader | Team Leaders |  |
| 7-8 weeks | Collection of tuition from workers | MD |  |
| 7 weeks | Requisition of supplies to Quartermaster | Mission Leader |  |
| 6 weeks | Quartermaster and MD work to make certain all necessary supplies are available. | Quartermaster and MD |  |
| 1 week | Assignment of cases to Team Leaders | Mission Leader |  |
| 4 days | Flight and Housing confirmations received | Participants and MD |  |
| 1 day | Final email to participants coordinating efforts | Mission Leader |  |
| 0 | Missioneration |  |  |
| + 2 days | Unused supplies returned to inventory or source, report of supplies/equipment used to MD | Quartermaster |  |
| + 1 week | Medical reports finished and turned in to Mission Leader Patient Signalment Dental Pathology & Treatment Chart Anesthetic Protocol | Team Leaders |  |
| + 1 week | Photos to Mission leader | All attendees |  |
| + 2 weeks | Photo compilation CD to all attendees | Mission Leader |  |
| +3 weeks | News release to JVD and other pertinent sites | MD |  |
| +3 weeks | Report on Mission – animals treated, supplies used, budget vs. actual to PEIVDF and PEVDAC | MD |  |